## Meeting
20260412_Internal Meeting IPS
Date | 2026-04-12
Time
Location
Type | Internal Meeting IPS
Status | Completed
Notes
Participants
Name | Company | Attendance
Owner | Group IPS | Present
Package Owner 1 | Group IPS | Present
Package Owner 2 |  | Absent
Architect |  | Present
TeamComReviewer |  | Absent
TeamTechReviewer |  | Absent

## Points
ID | Type | Topic | Details | Notes | Responsible | Due Date | Status | Closed At
MP-000003 | ACTION | Test |  |  | Package Owner 1 |  | Not Started
MP-000004 | ACTION | Test non participant 1 |  | Client - 2026-04-12 Test Administrator - 2026-04-22 fufyu Administrator - 2026-04-22 bhbik Administrator - 2026-04-22 vhbkj | Client |  | In Progress
MP-000005 | ACTION | Test non-participant 2 | 03/11/2025: Cellen van B2 en B4 bestellen deze week 13/11/2025: Technische fiche ter goedkeuring wordt doorgestuurd door IMTECH. Cellen moeten voor eind November besteld worden. 17/11/2025: Cellen B2 en B4 staan op Brycsis, moet deze week besteld worden We wachten op de beslissing van reservecel tot 19/11, zonder beslissing bestellen wij zonder reservecel. Beslissing over transfovermogen B2 en B2-FR ook beslist deze week (1MVA of 630kVA voor normaal en 1.6MVA of 1250kVA voor FR) Afmetingen AD2:700mm, AD3: 900mm, zijplaaten:37mm 24/11/2025: Doorlooptermijnen van de elektrische werken na te kijken door IMTECH voor B2-B4 + Omschakelplan OSA (detailplanning per vertrek op te maken) 01/12/2025: Meeting organiseren als Elecri de cablelijs (B2-B4) opmaakt (5-12/12) 15/12/2025: Wachten op Electri lijst & ALSB o |  | Bidder 4 |  | In Progress