## Work Permits
ID | Package | Title | Description | Start Date | End Date | Permit Types | Areas | Hazards | PPE | Status | Approved Areas | Rejected Areas | Area Approvals (detail) | Submitted By | Submitted At | Created By | Created At | Updated By | Updated At
WP-000020 | P002 | bsdf | vadf | 2026-04-23 | 2026-05-21 | Cold Work Permit, Hot Work Permit | A1, A3 | Electrical Danger, Fire Hazard, General danger, Hot surface, Toxic substances | Ear protection, Mask, Protective gloves, Safety clothing, Safety goggles, Safety helmet, Safety shoes, respiratory protection | CLOSED | A1, A3 |  | A1: APPROVED by Construction Manager on 2026-04-22 22:37 ¦ A3: APPROVED by Construction Manager on 2026-04-22 22:37 | Bidder 2 | 2026-04-22 22:36 | Bidder 2 | 2026-04-22 22:30 | Administrator | 2026-04-22 22:39
WP-000019 | CTG | Temporary site road widening | Widen the northern site access road to accommodate crane traffic. | 2025-08-25 | 2025-09-25 | Excavation Permit, Lifting Permit | A1 | Crusshing hazard, Lifting operations | Protective gloves, Safety goggles, Safety helmet, Safety shoes | CLOSED | A1 |  | A1: APPROVED by Construction Manager on 2025-08-25 12:00 | Bidder 1 | 2025-08-23 12:00 | Bidder 1 | 2025-08-22 12:00
WP-000018 | P001 | Stairwell handrail installation — Area 3 | Install galvanised steel handrails on the Area 3 emergency stairwell. | 2026-05-05 | 2026-05-20 | Cold Work Permit, Hot Work Permit, Work at Height Permit | A3 | Fire Hazard, Risk of Falling | Harness, Protective gloves, Safety goggles, Safety helmet, Safety shoes | DRAFT | [5 empty] | Bidder 1 | 2026-04-20 12:00
WP-000017 | P001 | Concrete core drilling — Area 1 floor slab | Core drill 8 penetrations through the Area 1 floor slab for ducting. | 2026-04-22 | 2026-05-05 | Cold Work Permit, LOTO Permit | A1 | Crusshing hazard, Electrical Danger | Ear protection, Protective gloves, Safety goggles, Safety helmet, Safety shoes | PENDING |  |  | A1: PENDING | Bidder 1 | 2026-04-17 12:00 | Bidder 1 | 2026-04-16 12:00
WP-000016 | P002 | Pump P-201 overhaul — Area 2 | Remove, overhaul and reinstall pump P-201 including alignment. | 2026-04-08 | 2026-04-30 | Cold Work Permit, LOTO Permit, Lifting Permit | A2, A3 | Electrical Danger, Hot surface, Lifting operations | Protective gloves, Safety goggles, Safety helmet, Safety shoes | REJECTED | A2 | A3 | A2: APPROVED by Package Owner 2 on 2026-04-05 12:00 ¦ A3: REJECTED by Construction Manager on 2026-04-06 12:00 — Lifting plan missing. Need crane load chart and rigging study before approval. | Bidder 2 | 2026-04-03 12:00 | Bidder 2 | 2026-04-01 12:00
WP-000015 | P001 | Roofing & weather-proofing — Area 1/2 | Membrane roofing and flashing works on Area 1 and Area 2 roofs. | 2026-02-15 | 2026-05-15 | Cold Work Permit, Hot Work Permit, Work at Height Permit | A1, A2 | Fire Hazard, Risk of Falling | Harness, Protective gloves, Safety clothing, Safety goggles, Safety helmet, Safety shoes | APPROVED | A1, A2 |  | A1: APPROVED by Administrator on 2026-04-22 17:18 ¦ A2: APPROVED by Administrator on 2026-04-22 17:18 | Bidder 1 | 2026-04-19 12:00 | Bidder 1 | 2026-02-05 12:00 |  | 2026-04-22 17:18
WP-000014 | P002 | Instrumentation cable pulls — Area 2 / Area 3 | Pull and terminate instrumentation cable trays between Area 2 and Area 3. | 2026-04-25 | 2026-05-30 | Cold Work Permit, Electrical Work Permit, LOTO Permit | A2, A3 | Electrical Danger, Risk of Falling | Harness, Protective gloves, Safety goggles, Safety helmet, Safety shoes | PENDING |  |  | A2: PENDING ¦ A3: PENDING | Bidder 2 | 2026-04-18 12:00 | Bidder 2 | 2026-04-15 12:00
WP-000013 | P001 | External cladding Area 3 — north façade | Install pre-fab aluminium cladding panels on the north face of Area 3. | 2026-01-15 | 2026-04-10 | Cold Work Permit, Work at Height Permit, Lifting Permit | A3 | Lifting operations, Risk of Falling | Harness, Protective gloves, Safety goggles, Safety helmet, Safety shoes | APPROVED | A3 |  | A3: APPROVED by Construction Manager on 2026-01-12 12:00 | Bidder 1 | 2026-01-10 12:00 | Bidder 1 | 2026-01-08 12:00
WP-000012 | P001 | Interior finishing — plaster & painting Area 1 | Plastering, primer and finishing coats on interior walls in Area 1. | 2026-03-01 | 2026-05-31 | Cold Work Permit, Work at Height Permit | A1 | Risk of Falling, Slippery surface | Harness, Protective gloves, Safety goggles, Safety helmet, Safety shoes | APPROVED | A1 |  | A1: APPROVED by Construction Manager on 2026-02-25 12:00 | Bidder 1 | 2026-02-22 12:00 | Bidder 1 | 2026-02-20 12:00
WP-000011 | P002 | Stainless piping hydro-test — process loop 2A | Hydrostatic test of SS piping loop in Area 2 up to design pressure. | 2026-03-10 | 2026-04-20 | Cold Work Permit, LOTO Permit, Pressure Testing Permit | A2 | Electrical Danger | Protective gloves, Safety goggles, Safety helmet, Safety shoes | CLOSED | A2 |  | A2: APPROVED by Package Owner 2 on 2026-03-09 12:00 | Bidder 2 | 2026-03-07 12:00 | Bidder 2 | 2026-03-05 12:00
WP-000010 | P001 | Structural steel erection phase 1 — columns grid A-E | Erection of steel columns and primary beams, including bolt-up of splices and grouting of base plates on Area 1. | 2025-10-05 | 2025-12-15 | Cold Work Permit, LOTO Permit, Work at Height Permit, Lifting Permit | A1, A3 | Crusshing hazard, Lifting operations, Risk of Falling | Harness, Protective gloves, Safety goggles, Safety helmet, Safety shoes | CLOSED | A1, A3 |  | A1: APPROVED by Construction Manager on 2025-10-02 12:00 ¦ A3: APPROVED by Construction Manager on 2025-10-02 12:00 | Bidder 1 | 2025-09-30 12:00 | Bidder 1 | 2025-09-28 12:00
WP-000009 | CTG | vefa | vfad | 2026-04-21 | 2026-04-21 | Cold Work Permit, Hot Work Permit | A2, A3 |  | Protective gloves, Safety goggles, Safety helmet, Safety shoes | APPROVED | A2, A3 |  | A2: APPROVED by Package Owner 2 on 2026-04-21 17:37 ¦ A3: APPROVED by Construction Manager on 2026-04-21 17:37 | Bidder 1 | 2026-04-21 17:37 | Bidder 1 | 2026-04-21 17:16 | Bidder 1 | 2026-04-21 17:37
WP-000008 | P001 | vsad | grwas | 2026-04-21 | 2026-04-21 | Cold Work Permit, Hot Work Permit | A1, A3 |  | Protective gloves, Safety goggles, Safety helmet, Safety shoes | APPROVED | A1, A3 |  | A1: APPROVED by Construction Manager on 2026-04-21 17:01 ¦ A3: APPROVED by Construction Manager on 2026-04-21 17:01 | Bidder 1 | 2026-04-21 15:27 | Construction Manager | 2026-04-21 15:16 | Bidder 1 | 2026-04-21 17:01
WP-000007 | CTG | vasdf | vafsd | 2026-04-21 | 2026-04-22 | Cold Work Permit, Hot Work Permit | A1 |  | Protective gloves, Safety goggles, Safety helmet, Safety shoes | PENDING |  |  | A1: PENDING | Bidder 1 | 2026-04-21 17:38 | Administrator | 2026-04-21 15:09 | Package Owner 2 | 2026-04-21 17:38
WP-000006 | CTG | dfs | vadf | 2026-04-21 | 2026-04-21 | Cold Work Permit, Hot Work Permit, Electrical Work Permit | A1 |  | Protective gloves, Safety goggles, Safety helmet, Safety shoes | APPROVED | A1 |  | A1: APPROVED by Construction Manager on 2026-04-22 22:30 | Administrator | 2026-04-21 15:00 | Administrator | 2026-04-21 14:37 | Administrator | 2026-04-22 22:30
WP-000005 | P001 | vfds | vfda | 2026-04-21 | 2026-04-21 | Cold Work Permit, Hot Work Permit, Confined Space Entry Permit, Electrical Work Permit, LOTO Permit, Excavation Permit, Work at Height Permit, Lifting Permit | A1, A2, A3 | Fire Hazard, General danger | Protective gloves, Safety goggles, Safety helmet, Safety shoes | DRAFT | [5 empty] | Administrator | 2026-04-21 14:06 | Administrator | 2026-04-21 14:31
WP-000004 | CTG | ,uktyg | ,yukg | 2026-04-21 | 2026-04-24 | Cold Work Permit | A1, A2 |  | Protective gloves, Safety goggles, Safety helmet, Safety shoes | APPROVED | A1, A2 |  | A1: APPROVED by Administrator on 2026-04-22 17:17 ¦ A2: APPROVED by Administrator on 2026-04-22 17:17 | Administrator | 2026-04-22 17:17 | Construction Manager | 2026-04-21 13:17 | Administrator | 2026-04-22 17:17
WP-000003 | CTG | jht | sbdf | 2026-04-21 | 2026-04-30 | Cold Work Permit | A1 |  | Protective gloves, Safety goggles, Safety helmet, Safety shoes | DRAFT | [5 empty] | Bidder 1 | 2026-04-21 13:12 | Administrator | 2026-04-21 13:13
WP-000002 | CTG | Test | Test nldsjvad; | 2026-04-21 | 2026-04-21 | Cold Work Permit | A1 |  | Protective gloves, Safety goggles, Safety helmet, Safety shoes | DRAFT | [5 empty] | Administrator | 2026-04-21 12:16 | Bidder 1 | 2026-04-21 13:07
WP-000001 | P001 | Works to do | Works to do | 2026-04-21 | 2026-05-08 | Cold Work Permit | A1, A2, A3 |  | Protective gloves, Safety goggles, Safety helmet, Safety shoes | DRAFT | [5 empty] | Administrator | 2026-04-21 10:57